## Gantt Chart - Manual Duration
Task Name | Start Date | End Date | Duration (Days) | Days Complete | Days Remaining | Percent Complete | Start Date in Number Form | 43021 | Use this number for the Minimum Bound of the Horizontal Axis to set the beginning of the chart.
Contact Client | 2017-10-13 | 2017-10-19 | 6 | 6 | 0 | 100%
Write Proposal | 2017-10-19 | 2017-10-20 | 1 | 0.55 | 0.45 | 55%
Meet with client | 2017-10-30 | 2017-11-04 | 5 | 5 | 0 | 100%
Meet with Sara | 2017-10-31 | 2017-11-03 | 3 | 3 | 0 | 100%
Finalize ER Diagram | 2017-11-08 | 2017-11-09 | 1 | 0.95 | 0.05 | 95%
Create/Delete/Populate Tables | 2017-11-08 | 2017-11-10 | 2 | 1.9 | 0.1 | 95%
Write Quirries/Triggers/Views | 2017-11-09 | 2017-11-11 | 2 | 1.8 | 0.2 | 90%
Meet with Client | 2017-11-14 | 2017-11-16 | 2 | 2 | 0 | 100%
Finalize ER Diagram | 2017-11-20 | 2017-11-22 | 2 | 2 | 0 | 100%
Finish Tables | 2017-11-20 | 2017-11-22 | 2 | 2 | 0 | 100%
Meet with Sara | 2017-11-19 | 2017-11-22 | 3 | 3 | 0 | 100%
Implement Quirries/Views in PHP | 2017-11-26 | 2017-11-29 | 3 | 0 | 3 | 0%
Make HTML/CSS for UI | 2017-11-25 | 2017-11-27 | 2 | 2 | 0 | 100%
Make Documentation | 2017-11-28 | 2017-11-30 | 2 | 0 | 2 | 0%
Prepare Presentation | 2017-11-28 | 2017-11-30 | 2 | 0 | 2 | 0%